## Gantt Chart (Editable)
Task | Owner | Status | Start Wk | Duration (wks) | Jun W1 | Jun W2 | Jun W3 | Jun W4 | Jul W1 | Jul W2 | Jul W3 | Jul W4 | Aug W1 | Aug W2 | Aug W3 | Aug W4
(week index →) |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Literature Review | Team | Completed | 1 | 1
Project Proposal | Team | Completed | 1 | 2
Floating-Point Softmax Model | Chenxi | Completed | 2 | 2
Fixed-Point PICO Softmax Model | Chenxi | Completed | 3 | 2
Hardware Architecture Design | Raaida / Mena | Completed | 2 | 3
RTL: Controller & Bus Interface | Chenxi | Completed | 5 | 2
RTL: Max Finder / Delta / Exp. Approx. | Raaida | Completed | 5 | 2
RTL: Divider & Output Buffer | Mena | Completed | 5 | 2
RTL Schematic Review | Team | Completed | 6 | 1
RTL Functional Simulation | Chenxi / Raaida | Completed | 6 | 2
Module Integration | Raaida / Chenxi | Completed | 7 | 2
Debugging | Team | Planned | 9 | 1
Compilation / Synthesis | Mena | Planned | 9 | 2
Timing Closure & Resource Analysis | Mena | Planned | 10 | 1
FPGA Deployment | Chenxi | Planned | 10 | 2
Hardware Validation | Mena / Raaida | Planned | 11 | 1
RTL-to-Gate Synthesis | Mena | Planned | 11
Chip Floorplanning | Team | Planned | 11
Power Planning | Chenxi | Planned
Placement Optimization | Chenxi / Raaida | Planned
Clock Tree Synthesis (CTS) | Mena | Planned
Routing | Raaida | Planned
Physical Verification | Team | Planned
Timing Closure | Team | Planned
GDSII Generation | Chenxi | Planned
Final Tapeout Package | Team | Planned
Performance Evaluation | Team | Planned
Final Documentation | Chenxi / Team | Planned
Final Demonstration | Team | Planned
Legend: | Completed | Ongoing | Planned
Note on M1: TODAY — RTL Functional Simulation just completed; Module Integration in progress.

## Gantt Chart (Visual)
PICO Softmax Hardware Accelerator — Project Gantt Chart
Fig. 1. Project Gantt chart for the PICO Softmax hardware accelerator, showing parallel task execution across the three-member team (Chenxi, Raaida, Mena) from June through August. Green denotes completed tasks, yellow denotes the task currently in progress, and blue denotes planned tasks; the dashed red line marks the current project date. With RTL functional simulation now complete, the remaining integration, synthesis, and validation tasks are distributed across concurrent, non-overlapping work streams that the three team members can execute in parallel, confirming the design goal is achievable with the currently available team.
This is a static picture for reference. To edit dates/status, use the 'Gantt Chart (Editable)' tab, which recolors automatically.

## Resource Allocation
Team Member | Responsibilities | Deliverables | Current Status (as of today)
Chenxi | • Floating-point Softmax reference model • Fixed-point PICO Softmax model • Controller RTL • Bus interface RTL • RTL functional simulation • Documentation lead | • Verified Python golden models (float & fixed-point) • Controller and bus-interface RTL modules • Passing functional simulation testbench | Algorithm models, Controller/Bus RTL, and functional simulation completed; now supporting module integration.
Raaida | • Max Finder unit • Delta unit • Exponential approximation unit • Datapath verification • RTL integration support | • Max Finder, Delta, and Exponential Approximation RTL modules • Datapath verification report | All three assigned RTL modules completed and verified; actively integrating datapath with controller.
Mena | • Divider unit • Output buffer • Quartus compilation • FPGA deployment • Hardware validation | • Divider and output-buffer RTL modules • Synthesized Quartus project (upcoming) • FPGA bitstream and validation plan (upcoming) | Divider and output-buffer RTL completed; preparing Quartus synthesis flow for next milestone.
Shared | • RTL integration • Debugging • Final verification • Final documentation • Final presentation | • Fully integrated and verified top-level design • Final report and demonstration | Module integration in progress; remaining shared tasks scheduled for August.

## Workload Distribution
Project Phase | Chenxi | Raaida | Mena
Algorithm Development | 3 | 1 | 1
RTL Design | 2 | 3 | 2
Simulation & Verification | 3 | 2 | 1
FPGA Validation | 1 | 2 | 3
Documentation | 3 | 1 | 2
Enter 1 (Low), 2 (Medium), or 3 (High) — the dot indicator updates automatically.
●●● High workload ●●○ Medium workload ●○○ Low workload